(EOTC) Year 10 Activity Week Team Meeting (Minutes)

(Boardroom, Monday 22nd November)

Present: SC, HK, ML, DS, CM, JT, IJ, JD, RH, LC, HN, TA.

Absent: BC, KH, BW, MH

Minutes by LC, RH, TA

Before the meeting

- Staff checked the activity roster and the duty team roster posted on the wall in the Boardroom and amended where required.

(TA to post modified rosters on to the wiki; copies to be sent to MA)

BUSINESS

Volunteers wanted

- Someone to address the Year 10 students at an assembly in the week prior to

Activity Week.

- TA

- Someone to contact Mihi Henare.  Is she still available? Has she arranged

senior students to help out?  Does she need any resources, help?

- AK has confirmed to TA that MH will be attending.  TA to email MH, let her know times, etc.

- Someone to take still photos of wearable arts and kapa haka.

- JT, Mon. – Thurs; HN on Fri.  Hilda to be approached for College camera.  JT to download pics on to College intranet (under ‘Staff Resources’) at the end of each day.

- Someone to take video footage of wearable arts and kapa haka.

- IJ to get camera from EW, tapes from HA, recharge batteries.

- Someone to get and return key for Nurses’ Hall.

- LC to arrange (see JP and /or KH)

- Someone to forward a report to the “Northland Age”  and the “Northern News”

(to include mention of Mitre 10, Monty Knights, Kaitaia Resource Recovery

Centre, thanking them for their cardboard contributions).

- IJ, HN.

- Someone to write letters of thanks to contributors of cardboard, Nurses’ Hall

people.

- TA

- Who has their First Aid Certificate? (to be on duty if swimming?).

- IJ, KH.  There was some discussion regarding the difficulties and advantages of arranging to have the pool made available, eg. need for qualified life-savers?  TA to discuss with CY.

- Someone to fine tune the duty roster.

- RH, JD

- Someone to take the roll (twice a day) and to pass them on to Judy.

- DS (Mon. – Thurs.) and SC on Friday.

Notes:

  - if you have taken on a job, arrange for someone else to do it on the day(s) when you are not attending.

  - officially, you don’t actually have a ‘day off’ unless you have notified the Principal or you are a part-timer.  Keep your colleagues informed about your movements.

Equipment needed

- Still digital camera (JT, HN)

- Video camera, digital film (IJ, English Department;  HA for digital video

tape.)

- Scissors, string, craft knives, old desks or tables for work space, brooms,

Other materials for Art to Wear.

- Joy to arrange

Decisions to make

- Do we have access to the pool?

Probably, KH following up.

- If we have access, do we use the pool?

General consensus was “yes.”

- If we use the pool, do we need RAMS forms filled out?

DS to complete.  TA to discuss with CY.

- Do we charge students to use the pool?

Only if the Nurses charge us

- Do we need RAMS forms even if we don’t use the pool?

TA to discuss with CY

Daily Procedures

A          Kapa Haka Days

- Assemble in the Hall at 8:45.

- Call the roll and inform students about expectations for the day.

- Collect, label and store students’ valuables.

- Accompany students to Nurses’ Hall, crossing the College fields to get there(?), staff to arrange themselves at strategic points along the way.

- Students to leave shoes at the Nurses’ Hall door, remove hats.

- Staff check for gum, cell-phones and gadgets on entry.

- If pool available, boys and girls to use at different times?  (Eg girls eat first, while boys swim)

- Roll call and clean-up after lunch.

- Security check on departure.

- Head counts throughout the day with extra roll calls if numbers are down.

B	Wearable Art Days

- Assemble in the Hall at 8:45.

- Call the roll and inform students about events of the day and expectations.

- Show the wearable art film clips

- Organise groups, distribute equipment

- Roll call again after lunch.

- Head counts throughout the day with extra roll calls if numbers are down.